## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-11 | Setup of Project (JDK spring boot) | MUST HAVE |  | vale vignesh | 3- Completed
S1 | S1 | US-12 | Implement Task CRUD using themeleaf UI | MUST HAVE | US-11 | vale vignesh | 3- Completed
S1 | S1 | US-13 | Add filter ,sorting and pagination in UI | MUST HAVE | US-12 | vale vignesh | 3- Completed
S2 | S2 | US-21 | Add enums(status,priority)+ UI improvements | MUST HAVE | US-12 | vale vignesh | 3- Completed
S2 | S2 | US-22 | Add REST APIs for Task CRUD | COULD HAVE | US-11 | vale vignesh | 3- Completed
S2 | S2 | US-23 | Add REST filtering,sorting and pagination | COULD HAVE | US-21 | vale vignesh | 3- Completed
S2 | S2 | US-24 | API testing via Postman+final cleanup | MUST HAVE | US-22 | vale vignesh | 3- Completed
S3 | S3 | US-31 | Authentication and authorisation | MUST HAVE | US-11 | vale vignesh | 3- Completed
S3 | S3 | US-32 | Integration of Email API | MUST HAVE | US-31 | vale vignesh | 3- Completed
S3 | S3 | US-33 | Implementing Session and Jason web token | MUST HAVE | US-32 | vale vignesh | 3- Completed
S4 | S4 | US-41 | Implementation of task tracking | MUST HAVE | US-12 | vale vignesh | 3- Completed
S4 | S4 | US-42 | Build dashboard with visuals analytics | MUST HAVE | US-41 | vale vignesh | 3- Completed
S4 | S4 | US-43 | Adding user profile and password management | MUST HAVE | US-41 | vale vignesh | 3- Completed
S4 | S4 | US-44 | Adding reminder settings export data | MUST HAVE | US-32 | vale vignesh | 3- Completed
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 53 | 6 | 13 | 19 | 12 | 22 | 19 | 16 | 13 | 8 | 17 | 25 | 10 | 8 | 23
SPRINT 1 BACKLOG
US-11 | T-1 | Downloading and installing JDK 17 spring boot setup | 2026-02-16 | 2026-02-18 | vale vignesh | setting up | 3- Completed | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-2 | Installing and setting up intellij and setting up project environment with spring boot | 2026-02-19 | 2026-02-20 | vale vignesh | setting up | 3- Completed | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-3 | Making TaskController and applying CRUD operations | 2026-02-23 | 2026-02-25 | vale vignesh | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-4 | Adding APIs pages for add,view,edit,delete and posting to github | 2026-02-26 | 2026-02-27 | vale vignesh | Coding | 3- Completed | 6 | 0 | 0 | 0 | 1 | 3 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0
US-12 | T-5 | Setting up sql and connecting to spring boot | 2026-03-02 | 2026-03-03 | vale vignesh | Coding | 3- Completed | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 0 | 1 | 0
US-13 | T-6 | Applying paginators ,filters and sorting | 2026-03-04 | 2026-03-05 | vale vignesh | Coding | 3- Completed | 2 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
US-21 | T-7 | Adding enum's and working on css,html | 2026-03-06 | 2026-03-09 | vale vignesh | Coding | 3- Completed | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 1
US-22 | T-8 | Adding RestController and Applying CRUD operations | 2026-03-09 | 2026-03-10 | vale vignesh | Coding | 3- Completed | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 3
US-23 | T-9 | Adding Rest APIs pages for add,view,edit,delete | 2026-03-10 | 2026-03-11 | vale vignesh | Coding | 3- Completed | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 3 | 0 | 1 | 2
US-23 | T-10 | Adding filters and sorting for Rest APIs | 2026-03-12 | 2026-03-13 | vale vignesh | Coding | 3- Completed | 3 | 0 | 0 | 2 | 2 | 1 | 0 | 3 | 1 | 0 | 1 | 1 | 0 | 0 | 2
US-24 | T-11 | API testing via postman | 2026-03-16 | 2026-03-17 | vale vignesh | Coding | 3- Completed | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 0 | 4
US-24 | T-12 | Few API addition and UI improvement | 2026-03-18 | 2026-03-20 | vale vignesh | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 1 | 2 | 1 | 0 | 1
US-31 | T-13 | Adding authcontroller | 2026-03-20 | 2026-03-23 | vale vignesh | Coding | 3- Completed | 2 | 1 | 3 | 1 | 0 | 2 | 1 | 0 | 0 | 1 | 2 | 2 | 3 | 1 | 4
US-32 | T-14 | Adding email service | 2026-03-24 | 2026-03-25 | vale vignesh | Coding | 3- Completed | 2 | 0 | 2 | 2 | 0 | 1 | 2 | 1 | 3 | 0 | 2 | 0 | 1 | 0 | 1
US-32 | T-15 | Implementing sending and verifying otp | 2026-03-26 | 2026-03-27 | vale vignesh | Coding | 3- Completed | 2 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 5 | 2 | 0 | 0
US-32 | T-16 | Working on frontend and Authenticating | 2026-03-30 | 2026-03-31 | vale vignesh | Coding | 3- Completed | 2 | 2 | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1
US-33 | T-17 | Implementing Sessions for task viewing of respective accounts | 2026-04-01 | 2026-04-02 | vale vignesh | Coding | 3- Completed | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 0 | 2 | 2
US-41 | T-18 | Implementing tracking systems based on status priority and duedates | 2026-04-03 | 2026-04-06 | vale vignesh | Coding | 3- Completed | 1 | 1 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 2
US-42 | T-19 | Adding a dashboard overview for tracking | 2026-04-06 | 2026-04-04 | vale vignesh | Coding | 3- Completed | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-42 | T-20 | Working on frontend for task overview and record tasks | 2026-04-07 | 2026-04-07 | vale vignesh | Coding | 3- Completed | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-43 | T-21 | Securing otp and password with bcrypt and adding security config | 2026-04-08 | 2026-04-08 | vale vignesh | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-43 | T-22 | Adding profile and edit profile details | 2026-04-09 | 2026-04-09 | vale vignesh | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-44 | T-23 | Adding remainder setting | 2026-04-10 | 2026-04-10 | vale vignesh | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-44 | T-24 | Adding calendar view and improving visuals with list view and card view | 2026-04-10 | 2026-04-13 | vale vignesh | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
US-44 | T-25 | Implementing export option through email and download options | 2026-04-13 | 2026-04-13 | vale vignesh | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9/15/2016 or 15-Sep-2016
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9/15/2016 or 15-Sep-2016
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the total task estimated in hours for all the user stories
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 1 work
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 2 work
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 3 work
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 4 work
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 5 work
Note on O3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 6 work
Note on P3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 7 work
Note on Q3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 8 work
Note on R3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 9 work
Note on S3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 10 work
Note on T3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 11 work
Note on U3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 12 work
Note on V3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 13 work
Note on W3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | sprint 1 | 2026-02-16 | 2026-02-27 | vale vignesh | improving the task management System |  | UI Improvements | worked on add, edit, delete and filters and sorting
2 | sprint 2 | 2026-03-02 | 2026-03-13 | vale vignesh | implementation of Rest api |  | Testing | implemented RestController and starting testing
3 | sprint 3 | 2026-03-16 | 2026-03-27 | vale vignesh | implementation of authentication and authorisation |  | Testing and verifying | Providing user login, sign up options and making sure they work properly
4 | sprint 4 | 2026-03-30 | 2026-04-13 | vale vignesh | improvement of UI and dashboard implementation |  | UI Improvements | improving the UI and adding dashboard and reminder options
5
6
7